## A
World in Flames Artificial Intelligence Opponent
Game Phase, Subphase, Etc. | Rules Section | Implementator | Task | Task # | Implementation Method | AIO Decision | Progress | Status
pSetup, | RAW 24. | See Subphases Below | [5 empty] | Done
suspLendLease, |  | Not in Barbarossa | [5 empty] | Done
suspMajorPowers, |  | AIO | Scrap units pre-DOW |  | AIO_Scrap_USSR.SCP |  |  | Done
|  | AIO | Select Air units |  | Hard coded (take best) |  |  | Done
|  | AIO | Place Naval units on map |  | AIO_Setup_USSR.SET |  |  | Done
|  | AIO | Place Air units on map | 1 | LAIO Script |  | Script written
|  | AIO | Place Land units on map | 2 | LAIO Script |  | Script written
suspPartisans, |  | Not in Barbarossa | [5 empty] | Done
pReinforcement, | RAC 4. | See Subphases Below | [5 empty] | Done
RspAnnualAdds, | RAC 4.1.1 & 4.1.2. | MWIF Process | [5 empty] | Done
RspScrap, | RAC 4.1.3. | AIO | Scrap units post-DOW |  | Hard coded - none | Hard coded - none |  | Done
RspReplacements, | RAC 4.1.4. | Not in Barbarossa | [5 empty] | Done
RspAirReserve, | RAC 14.6.1. | AIO | Assign Pilots | 3 | Take the best available. | AFGS 1 | Branching logic
RspPlaceUnits, | RAC 4.2. | AIO | Place Air units on map | 4 | LAIO Script | AFGS 2, AFGS 3, AM 1, AM 2 | Branching logic
|  | AIO | Place Land units on map | 5 | LAIO Script | FM 3, FM 4 | Branching logic
RspRemoveAir, | RAC 14.6.1. | AIO | Remove Air units from map | 6 |  | AFGS 3 | Branching logic
pLending, | RAC 5. | Not in Barbarossa | [5 empty] | Done
pInitiative, | RAC 6. | AIO | Decide on reroll | 7 | Hard coded - always ask for reroll. | GS 3 |  | Done
|  | AIO | Decide to move first |  | Hard coded - always move first. | GS 3 |  | Done
pWeather, | RAC 8. | MWIF Process | [5 empty] | Done
pDeclareWar, | RAC 9. | See Subphases Below | [5 empty] | Done
DspDOWMajor, | RAC 9.2 & 9.3. | Not in Barbarossa | [5 empty] | Done
DspDOWMinor, | RAC 9.2, 9.3, 9.10, & 13.3.2 (#7 & #44). | Not in Barbarossa | [5 empty] | Done
DspUSEntry, | RAC 9.4. | Not in Barbarossa | [5 empty] | Done
DspNeutralityPacts, | RAC 9.5. | Not in Barbarossa | [5 empty] | Done
DspReserves, | RAC 9.6. | AIO | Place Land units on map | 8 | LAIO Script | JCS 4 | Script written
DspChooseAligner, | RAC 9.7. | Not in Barbarossa | [5 empty] | Done
DspSetupAttackedMinor, | RAC 9.7. | Not in Barbarossa | [5 empty] | Done
DspAlignMinor, | RAC 9.8. | Not in Barbarossa | [5 empty] | Done
DspSetupAlignedMinor, | RAC 9.8. | Not in Barbarossa | [5 empty] | Done
pChooseAction, | RAC 10. | AIO | Choose Action | 9 | Hard coded - Land; Script for using O-Chit. | JCS 1, JCS13 | Branching logic
pPortAttack, | RAC 11.2. | See Subphases Below | [5 empty] | Done | AD - Admiralty | Navy - 1
AspCAP, | RAC 14.2.1. | AIO |  | 10 | Hard coded - none | AFC 10 |  | Done | AFC - Air Fleet Commander | Air Force - 3 - AO
AspFlyA, | RAC 14.2.2, 14.2.3, & 14.2.1. | AIO |  | 11 | Hard coded - none | AFC 1, FA 5, AFC 10 |  | Done | AFGS - Air Force General Staff | Air Force - 1
AspInterceptD, | RAC 14.2.1. | AIO |  | 12 | Hard coded - none | AFC 10 |  | Done | AM - Air Marshal | Air Force - 2 - TO
AspInterceptA, | RAC 14.2.1. | Not in Barbarossa |  |  |  | AFC 10 |  | Done | AGS - Army General Staff | Army - 1
AspSurprise, | RAC 11.5.6 | AIO | Commit subs | 13 | Hard coded - Do not commit subs | FA 8 |  | Done | AGC - Army Group Comander | Army - 3 - AO
AspAirAir, | RAC 14.3. | See Sub-Subphases Below | [5 empty] | Done | CIC - Commander in Chief | Major Power - 2
| RAC 11.5.6 | AIO | Surprise points: Avoid, Air-to-air | 14 | Hard coded - Avoid combat | FA 11 |  | Done | CG - Commanding General | Army - 4 - LR
sspLocation, | RAC 14.3. | AIO |  |  | Hard coded - given order | Hard coded - given order |  | Done | FM - Field Marshal | Army - 2 - TO
sspArrange, | RAC 14.3.1. | AIO |  |  | Hard coded - given order | AFC 2 |  | Done | FA - Fleet Admiral | Navy - 4 - SA
sspRollDef, | RAC 14.3.2. | MWIF Process | [5 empty] | Done | FL - Foreign Liaison | Major Power 4
ssp1stUnit, | RAC 14.3.3. | AIO |  | 17 |  | AFC 4 | Branching logic |  | GS - Grand Strategist | Major Power - 1
ssp1stDisposition, | RAC 14.3.3. | AIO |  | 18 | Aborted air unit | AM 2 | Branching logic |  | JCS - Joint Chiefs of Staff | Major Power 5
sspRollAtt, | RAC 14.3.2. | MWIF Process | [5 empty] | Done | MC - Manufacturing Council | Major Power 3
ssp2ndUnit, | RAC 14.3.3. | AIO |  | 19 |  | AFC 4 | Branching logic |  | RA - Rear Admiral | Navy - 2 - TO
ssp2ndDisposition, | RAC 14.3.3. | AIO |  | 20 | Aborted air unit | AM 2 | Branching logic |  | SAC - Sea Area Commander | Navy - 3 - SAG
sspAttAbortStay, | RAC 14.3.2. | AIO |  | 21 |  | AFC 3 | Branching logic |  | SO - Special Operaions | Major Power 6
sspDefAbortStay, | RAC 14.3.2. | AIO |  | 22 |  | AFC 3 | Branching logic
sspBothStaying | RAC 14.3.2. | MWIF Process | [5 empty] | Done
AspAntiAirD, | RAC 11.5.9. | AIO |  | 23 | Hard coded: Land - none. | CG 20 |  | Done
| RAC 11.5.6 | AIO | Surprise points: AA Fire | 24 | Hard coded - increase AA Fire | FA 11 |  | Done
AspAttack, | RAC 11.5.9 | MWIF Process | [5 empty] | Done
| RAC 11.5.6 | AIO | Surprise points: NCC, Select | 26a | Hard coded - no surprise points should remain | FA 11 |  | Done
|  | AIO | Choose naval unit receiving damage | 26b | Hard coded - given order | FA 7 | Branching logic
AspReturnA, | RAC 14.2. | Not in Barbarossa |  |  |  | AM 2 | Branching logic | Done
AspReturnD, | RAC 14.2. | Not in Barbarossa |  |  |  | AM 2 | Branching logic | Done
pNavalAir | RAC 11.3. | Not in Barbarossa | [5 empty] | Done
pNavalMovement, | RAC 11.4. | Not in Barbarossa | [5 empty] | Done
pNavalCombatA, | RAC 11.5. | See Subphases Below | [5 empty] | Done
NCspChooseSeaArea, | RAC 11.5.2. | Not in Barbarossa | [5 empty] | Done
NCspNavalAirSupportA, | RAC 11.5.3. | Not in Barbarossa | [5 empty] | Done
NCspNavalAirSupportD, | RAC 11.5.3. | Not in Barbarossa | [5 empty] | Done
NCspCommitSubs, | RAC 11.5.4. | Not in Barbarossa | [5 empty] | Done
NCspSearch, | RAC 11.5.5. | Not in Barbarossa | [5 empty] | Done
NCspWaltherAbort, | RAC 22.4.19. | Not in Barbarossa | [5 empty] | Done
NCspIncludeSeaBoxes, | RAC 11.5.5. | Not in Barbarossa | [5 empty] | Done
NCspIncludeUSUnits, | RAC 13.3.2, US Entry Option #32. | Not in Barbarossa | [5 empty] | Done
NCspSurprise, | RAC 11.5.6. | Not in Barbarossa | [5 empty] | Done
NCspChooseType, | RAC 11.5.7 & 11.5.6. | Not in Barbarossa | [5 empty] | Done
NCspAirAir, | RAC 11.5.9 & 11.5.6. | Not in Barbarossa | [5 empty] | Done
NCspKamikaze, | RAC 14.8. | Not in Barbarossa | [5 empty] | Done
NCspAntiAirD, | RAC 11.5.9 & 11.5.6. | Not in Barbarossa | [5 empty] | Done
NCspAntiAirA, | RAC 11.5.9 & 11.5.6. | Not in Barbarossa | [5 empty] | Done
NCspNavalAirA, | RAC 11.5.9 & 11.5.6. | Not in Barbarossa | [5 empty] | Done
NCspNavalAirD, | RAC 11.5.9 & 11.5.6. | Not in Barbarossa | [5 empty] | Done
NCspASWPreFireD, | RAC 22.4.19. | Not in Barbarossa | [5 empty] | Done
NCspASWPreFireA, | RAC 22.4.19. | Not in Barbarossa | [5 empty] | Done
NCspSurfaceA, | RAC 11.5.8 & 11.5.6. | Not in Barbarossa | [5 empty] | Done
NCspSurfaceD, | RAC 11.5.8 & 11.5.6. | Not in Barbarossa | [5 empty] | Done
NCspASWD, | RAC 11.5.10, 22.4.19, & 11.5.6. | Not in Barbarossa | [5 empty] | Done
NCspSubA, | RAC 11.5.10 & 11.5.6. | Not in Barbarossa | [5 empty] | Done
NCspASWA, | RAC 11.5.10, 22.4.19, & 11.5.6. | Not in Barbarossa | [5 empty] | Done
NCspSubD, | RAC 11.5.10 & 11.5.6. | Not in Barbarossa | [5 empty] | Done
NCspEndRound, | RAC 11.5.11. | Not in Barbarossa | [5 empty] | Done
NCspAbortA, | RAC 11.5.11 (attacker voluntary abort) | Not in Barbarossa | [5 empty] | Done
NCspAbortD, | RAC 11.5.11 (defender voluntary abort). | Not in Barbarossa | [5 empty] | Done
NCspNextRound | RAC 11.5.11. | Not in Barbarossa | [5 empty] | Done
pNavalCombatD, | RAC 11.6. | Not in Barbarossa | [5 empty] | Done
pStrategicBombardment, | RAC 11.7. | See Subphases Below | [5 empty] | Done
AspCAP, | RAC 14.2.1. | AIO |  | 27 | Hard coded - none | AM 4 |  | Done
AspFlyA, | RAC 14.2.2, 14.2.3, & 14.2.1. | AIO |  | 28 | Hard coded - none | AFC 1, AM 3, AM 4 |  | Done
AspInterceptD, | RAC 14.2.1. | AIO |  | 29 | Hard coded - none | AM 4 |  | Done
AspInterceptA, | RAC 14.2.1. | Not in Barbarossa |  |  |  | AM 4 | Branching logic | Done
AspAirAir, | RAC 14.3. | See Sub-Subphases For Port Attacks | [5 empty] | Done
AspAntiAirD, | RAC 11.5.9. | AIO |  | 30 | Hard coded - none | CG 20 |  | Done
AspAttack, | RAC 11.7 | MWIF Process | [5 empty] | Done
AspReturnA, | RAC 14.2. | Not in Barbarossa |  |  |  | AM 2 | Branching logic | Done
AspReturnD, | RAC 14.2. | Not in Barbarossa |  |  |  | AM 2 | Branching logic | Done
pCarpetBombing, | RAC 11.8. | Not in Barbarossa |  |  |  | AFC 1, CG 17, AFC 11 | Branching logic | Done
pGroundStrike, | RAC 11.9. | See Subphases Below | [5 empty] | Done
AspCAP, | RAC 14.2.1. | AIO |  | 31 |  | AFC 7 | Branching logic
AspFlyA, | RAC 14.2.2, 14.2.3, & 14.2.1. | AIO |  | 32 |  | AFC 1, CG 11, AFC 7 | Branching logic
AspInterceptD, | RAC 14.2.1. | AIO |  | 33 |  | AFC 7 | Branching logic
AspInterceptA, | RAC 14.2.1. | AIO |  | 34 |  | AFC 7 | Branching logic
AspAirAir, | RAC 14.3. | See Sub-Subphases For Port Attacks | [5 empty] | Done
AspAntiAirD, | RAC 11.5.9. | AIO |  | 35 |  | CG 20 | Script written
AspAttack, | RAC 11.9 | MWIF Process | [5 empty] | Done
AspReturnA, | RAC 14.2. | AIO |  | 36 |  | AM 2 | Branching logic
AspReturnD, | RAC 14.2. | AIO |  | 37 |  | AM 2 | Branching logic
pRailMovement, | RAC 11.10. | AIO |  | 38 |  | JCS 5 | Branching logic
pLandMovement, | RAC 11.11. | AIO |  | 39 |  | FM 1-4, AGC 1-4/6/7, CG 1-10/12 | Branching logic
pAirTransport, | RAC 11.12. | See Subphases Below | [5 empty] | Done
AspCAP, | RAC 14.2.1. | AIO |  | 40 | Hard coded - none. | AFC 9 |  | Done
AspFlyA, | RAC 14.2.2, 14.2.3, & 14.2.1. | AIO |  | 41 |  | AFC 1, CG 21, AFC 9 | Branching logic
AspInterceptD, | RAC 14.2.1. | AIO |  | 42 | Hard coded - none. | AFC 9 |  | Done
AspInterceptA, | RAC 14.2.1. | AIO |  | 43 |  | AFC 9 | Branching logic
AspAirAir, | RAC 14.3. | See Sub-Subphases For Port Attacks | [5 empty] | Done
AspAntiAirD, | RAC 11.5.9. | AIO |  | 44 |  | CG 20 |  | Done
AspAttack, | RAC 11.12 | AIO |  | 45 |  | Never perform air transport. |  | Done
AspReturnA, | RAC 14.2. | AIO |  | 46 |  | AM 2 | Branching logic
AspReturnD, | RAC 14.2. | AIO |  | 47 |  | AM 2 | Branching logic
pUnloadLandUnits, | RAC 11.13. | Not in Barbarossa | [5 empty] | Done
pInvasion, | RAC 11.14. | Not in Barbarossa | [5 empty] | Done
pParadrop, | RAC 11.15. | See Subphases Below | [5 empty] | Done
AspCAP, | RAC 14.2.1. | AIO |  | 48 |  | AFC 12 | Branching logic
AspFlyA, | RAC 14.2.2, 14.2.3, & 14.2.1. | Not in Barbarossa |  |  |  | AFC 1, CG22, AFC 12 | Branching logic | Done
AspInterceptD, | RAC 14.2.1. | AIO |  | 49 |  | AFC 12 | Branching logic
AspInterceptA, | RAC 14.2.1. | Not in Barbarossa |  |  |  | AFC 12 | Branching logic | Done
AspAirAir, | RAC 14.3. | See Sub-Subphases For Port Attacks | [5 empty] | Done
AspAntiAirD, | RAC 11.5.9. | AIO |  | 50 |  | CG 20 |  | Done
AspAttack, | RAC 11.15 | MWIF Process | [5 empty] | Done
AspReturnA, | RAC 14.2. | AIO |  | 51 |  | AM 2 | Branching logic
AspReturnD, | RAC 14.2. | AIO |  | 52 |  | AM 2 | Branching logic
pLandCombatDeclaration, | RAC 11.16.1. | AIO |  | 53 |  | JCS10 | Branching logic
pIgnoreNotional, | RAC 11.14. | AIO |  | 54 |  | Whether to include notional units |  | Done
pEmergencyHQSupply, | RAC 2.4.3. | AIO |  | 55 |  | Whether to use emergency supply |  | Done
pShoreBombardmentD, | RAC 11.16.2. | Not in Barbarossa |  |  |  | CG 19 |  | Done
pShoreBombardmentA, | RAC 11.16.2. | Not in Barbarossa |  |  |  | CG 19 |  | Done
pHQSupportD, | RAC 11.16.3. | AIO |  | 56 |  | AGC 5 | Branching logic
pHQSupportA, | RAC 11.16.3. | AIO |  | 57 |  | AGC 5 | Branching logic
pGroundSupport, | RAC 11.16.4. | See Subphases Below | [5 empty] | Done
AspCAP, | RAC 14.2.1. | AIO |  | 58 |  | AFC 6 | Branching logic
AspFlyA, | RAC 14.2.2, 14.2.3, & 14.2.1. | AIO |  | 59 |  | AFC 1, CG12, AFC 6 | Branching logic
AspFlyD, | RAC 14.2.2, 14.2.3, & 14.2.1. | AIO |  | 60 |  | AFC 1, CG12, AFC 6 | Branching logic
AspInterceptD, | RAC 14.2.1. | AIO |  | 61 |  | AFC 6 | Branching logic
AspInterceptA, | RAC 14.2.1. | AIO |  | 62 |  | AFC 6 | Branching logic
AspAirAir, | RAC 14.3. | See Sub-Subphases For Port Attacks | [5 empty] | Done
AspAntiAirD, | RAC 11.5.9. | AIO |  | 63 |  | CG 20 | Branching logic
AspAntiAirA, | RAC 11.5.9. | AIO |  | 64 |  | CG 20 | Branching logic
AspAttack, | RAC 11.16.4. | MWIF Process | [5 empty] | Done
AspReturnA, | RAC 14.2. | AIO |  | 65 |  | AM 2 | Branching logic
AspReturnD, | RAC 14.2. | AIO |  | 66 |  | AM 2 | Branching logic
pLandCombatResolution, | RAC 11.16.5 & 11.16.6. | See Subphases Below | [5 empty] | Done
LCRspLandCombatSelection, | RAC 11.16.5. | AIO |  | 67 |  | CG 16 | Branching logic
LCRspDefSnowUnits, | RAC 8.2.7. | AIO |  | 68 |  | CG 10 | Branching logic
LCRspAttSnowUnits, | RAC 8.2.7. | AIO |  | 69 |  | CG 10 | Branching logic
LCRspChooseCombatType, | RAC 11.16.5 & 11.16.6. | AIO |  | 70 |  | CG 13 | Branching logic
LCRspLandCombatResolution, | RAC 11.16.5 & 11.16.6. | MWIF Process | [5 empty] | Done
LCRspConvertShattered, | RAC 11.16.5. | AIO |  | 71 |  | CG 18 | Branching logic
LCRspAssignLosses, | RAC 11.16.5. | AIO |  | 72 |  | CG 18 | Branching logic
LCRspHexControl, | RAC 11.11.6 (overruns) | MWIF Process | [5 empty] | Done
LCRspRetreats, | RAC 11.16.5. | AIO |  | 73 |  | CG 14 | Branching logic
LCRspAdvanceAfterCombat | RAC 11.16.5. | AIO |  | 74 |  | CG 15 | Branching logic
pAirRebase, | RAC 11.17. | AIO |  | 75 |  | AFGS 3, AM 2, | Branching logic
pAirReorganization, | RAC 11.18.1. | See Subphases Below | [5 empty] | Done
AspCAP, | RAC 14.2.1. | AIO |  | 76 |  | AFC 8 | Branching logic
AspFlyA, | RAC 14.2.2, 14.2.3, & 14.2.1. | AIO |  | 77 |  | AFC 1, FM 6, AFC 8 | Branching logic
AspInterceptD, | RAC 14.2.1. | AIO |  | 78 |  | AFC 8 | Branching logic
AspInterceptA, | RAC 14.2.1. | AIO |  | 79 |  | AFC 8 | Branching logic
AspAirAir, | RAC 14.3. | See Sub-Subphases For Port Attacks | [5 empty] | Done
AspAntiAirD, | RAC 11.5.9. | AIO |  | 80 |  | CG 20 |  | Done
AspAttack, | RAC 11.18.1. | AIO |  | 81 |  | FM 6 | Branching logic
AspReturnA, | RAC 14.2. | AIO |  | 82 |  | AM 2 | Branching logic
AspReturnD, | RAC 14.2. | AIO |  | 83 |  | AM 2 | Branching logic
pHQReorganization, | RAC 11.18.2. | AIO |  | 84 |  | FM 5 | Branching logic
pTRSSupply, | RAC 11.18.3. | Not in Barbarossa |  | 85 |  | FM 7 | Branching logic
pEndOfAction, | RAC 12. | MWIF Process | [5 empty] | Done
End of Turn Phases |  | See End of Turn Phases Below | [5 empty] | Done
pPartisan, | RAC 13.1. | AIO |  | 86 |  | AGC 7 | Branching logic
pEntry, | RAC 13.2. | Not in Barbarossa | [5 empty] | Done
pUSEntry, | RAC 13.3. | Not in Barbarossa | [5 empty] | Done
pProdPlanningPrelim, | RAC 13.6.1 & 13.6.2. | AIO |  | 87 |  | MC 2 | Branching logic
pStayAtSeaA, | RAC 13.4. | Not in Barbarossa | [5 empty] | Done
pStayAtSeaD, | RAC 13.4. | Not in Barbarossa | [5 empty] | Done
pReturnToBaseA, | RAC 13.4. | Not in Barbarossa | [5 empty] | Done
pReturnToBaseD, | RAC 13.4. | Not in Barbarossa | [5 empty] | Done
pUseOil, | RAC 13.5.1. | AIO |  | 88 |  | MC 13 | Branching logic
pFinalReorganization, | RAC 13.5. | MWIF Process | [5 empty] | Done
pBreakDown, | RAC 22.4.1. | AIO |  | 89 |  | AGC 8 | Branching logic
pProdPlanningFinal, | RAC 13.6.1 & 13.6.2. | AIO |  | 90 |  | MC 2 | Branching logic
pSearchAndSeizure, | RAC 13.6.1. | Not in Barbarossa | [5 empty] | Done
pScrapDestroyed, | RAC 13.6.9. | AIO |  |  | Hard coded to None |  |  | Done
pNavalRepair, | RAC 13.6.5. | Not in Barbarossa |  | 0 |  |  |  | Done
pProduction, | RAC 13.6.3 -> 13.6.9. | AIO |  | 91 |  | MC 2, MC 3 | Branching logic
pReform, | RAC 22.4.1. | AIO |  | 92 |  | AGC 8 | Branching logic
pIntelligence, | RAC 22.1. | Not in Barbarossa | [5 empty] | Done
pUkraine, | RAC 19.12. | Not in Barbarossa | [5 empty] | Done
pConquest, | RAC 13.7.1. | Not in Barbarossa | [5 empty] | Done
pMinorSupport, | RAC 13.7.2. | Not in Barbarossa |  | 3 |  |  |  | Done
pMutualPeace, | RAC 13.7.3. | Not in Barbarossa | [5 empty] | Done
pVichy, | RAC 13.7.4. | Not in Barbarossa | [5 empty] | Done
pLiberation, | RAC 13.7.5. | AIO | Liberate? Yes/No | 93 | Hard Coded - Yes |  |  | Done
pSurrender, | RAC 13.7.6. | AIO | Surrender? Yes/No | 94 | Hard Coded - No |  |  | Done
pFactoryDestruction, | RAC 22.2. | Not in Barbarossa | [5 empty] | Done
pVictory, | RAC 13.8. | AIO |  | 95 | Hard Coded - Do not open the form |  |  | Done
Digressions |  | See Digressions Below | [5 empty] | Done
digRelocate |  | Not in Barbarossa | [5 empty] | Done
digOverrun |  | AIO |  | 96 | Air and naval units overrun. | AM #2 | Branching logic
digReturnToBase |  | AIO |  | 97 | Air units aborted from air-to-air combat. | AM #2 | Branching logic
digNavalInterception |  | Not in Barbarossa | [5 empty] | Done
digNavalCombatAbort |  | Not in Barbarossa | [5 empty] | Done
digFixOverstacking |  | AIO |  | 98 | Destroy the first uniyt |  |  | Done
digCollapseVichy |  | Not in Barbarossa | [5 empty] | Done